## Site Review Checklist
Guest Room Supplies Pre-Purchase Site Review Checklist
Complete before RFQ, sample approval, or purchase-order release. Keep evidence references with the procurement approval file.
Property / Project |  |  | Document revision |  |  | Status summary
Review date |  |  | Representative rooms |  |  | Verified | Open Issue | Hold | Not Applicable | Not Reviewed
Review lead |  |  | Target release gate | RFQ / Sample / Purchase Order |  | 0 | 0 | 0 | 0 | 26
ID | Review Area | Field Check | Acceptance Evidence | Primary Owner | Status | Assigned To | Due Date | Room / Area | Evidence Reference | Notes
1 | Document control | Current drawing, schedule, item code, room code, and revision agree | Controlled review pack and revision register | Project manager | Not Reviewed
2 | Room coverage | Every materially different room type and known exception is included | Room-type sampling list | Operations / design | Not Reviewed
3 | Existing vs. future condition | Finished, unfinished, temporary, and scheduled-to-change conditions are identified | Status note linked to milestone | Project manager | Not Reviewed
4 | Niche and casegoods | Finished opening width, height, depth, level, squareness, and ventilation are verified | Dimensioned photograph or drawing markup | Design / engineering | Not Reviewed
5 | Counter and shelf placement | Footprint, edge clearance, stability, heat, splash, and cleaning access are confirmed | Placement test with approved sample or template | Housekeeping / design | Not Reviewed
6 | Doors and moving elements | Product does not conflict with doors, drawers, curtains, screens, hinges, or handles | Swing and movement test record | Design | Not Reviewed
7 | Circulation | Placement preserves required circulation and normal luggage use | Annotated plan and field photograph | Design / accessibility reviewer | Not Reviewed
8 | Guest reach and operation | Controls, handles, refills, and removable parts can be reached and operated as required | Full installed-arrangement review | Accessibility reviewer / operations | Not Reviewed
9 | Wall and backing | Substrate, backing, load, fixing zone, and permitted drilling are confirmed | Installer-approved fixing detail | Contractor / engineering | Not Reviewed
10 | Waterproofing and wet zones | Penetration limits, seals, splash exposure, and making-good responsibility are defined | Approved wet-area installation detail | Contractor / design | Not Reviewed
11 | Electrical supply | Voltage, frequency, receptacle, circuit, switching, and outlet position are verified | Engineer-approved connection schedule | Engineering | Not Reviewed
12 | Cord and reset access | Cord length, routing, isolation, reset, replacement, and cleaning access are workable | Operational placement trial | Engineering / housekeeping | Not Reviewed
13 | Ventilation and heat | Manufacturer clearances and room conditions can be achieved | Dimensioned clearance record | Engineering | Not Reviewed
14 | Data and system interface | Network, gateway, commissioning, credentials, privacy, updates, and offline behavior are assigned | Approved integration note | IT / engineering | Not Reviewed
15 | Product compatibility | Liners, refills, batteries, filters, brackets, trays, spare parts, and consumables match | Compatibility schedule and sample references | Procurement / operations | Not Reviewed
16 | Cleaning and chemicals | Actual cleaning tools, chemicals, temperatures, and handling method are suitable | Housekeeping trial and care approval | Housekeeping | Not Reviewed
17 | Maintenance access | Serviceable parts can be reached without destructive removal or excessive room downtime | Maintenance demonstration | Engineering | Not Reviewed
18 | Storage and pantry fit | Inner packs and cartons fit shelves, carts, lifts, and issue procedures | Pack dimensions and storage test | Housekeeping / stores | Not Reviewed
19 | Loading and delivery route | Dock, vehicle, unloading, corridor, elevator, doors, protection, and delivery hours are verified | Route survey with limiting dimensions | Logistics / contractor | Not Reviewed
20 | Installation workspace | Staging, assembly, charging, kitting, waste, and room-release space are assigned | Installation method statement | Installer / operations | Not Reviewed
21 | Packaging and room packs | Pack unit, labels, room-type segregation, carton weight, and disposal plan are defined | Approved packaging specification | Procurement / logistics | Not Reviewed
22 | Quantity basis | Room count, room mix, installed quantity, operational spares, and phased releases use the same revision | Reconciled quantity schedule | Procurement / operations | Not Reviewed
23 | Scope and responsibility | Supply, freight, customs, unloading, assembly, installation, commissioning, protection, and making good have owners | Responsibility matrix | Project manager / procurement | Not Reviewed
24 | Compliance hold points | Required destination, safety, accessibility, electrical, material, hygiene, and labeling checks are assigned | Category-specific compliance register | Project compliance owner | Not Reviewed
25 | Open issues | Every unresolved item has an owner, due date, impact, and procurement hold point | Open-issue register | Project manager | Not Reviewed
26 | Final baseline | Updated drawings, schedule, sample record, quotation assumptions, and purchase terms agree | Signed review release and revision set | Procurement / project sponsor | Not Reviewed